KEMPTON PROJECT MEETING

JUNE 15, 2017

AJH, RDO, LMS, DC, SDC, BB, MKP

1. Publishing in 2018 has become an unreachable goal.

AJH proposal: publish in 2020, assembly year and 250 years since the Last Judgment

\*\*\*\*\*

Rough out new timetable:

(Break remaining books (OT) into law, historicals, prophets)

Mid-March 2020: Printed and in hand (depends)

Mid-January2020: pdf’s sent to printer

Beginning of December: pdf’s ready to proof for formatting

Beginning of September: hand out proofreader copies for Prophets & miscl.

(summer work 2019--go over proofer copies for law & Josh-Kings)

March 2019: Hand out proofer copies for Law (Torah)

January 2019: Hand out proofer copies for the Josh-Kings

(Fall 2018: get proofer copies ready)

Fall 2017: Continue working on Psalms & NT

(Summer work 2017: Psalms & NT proofer comments, pink comments, proposals)

\*\*\*\*\*

AJH: We need to take into account added cost of extending the time. Will have to do some fundraising to get enough to cover publishing costs.

This summer we should take a look at costs overall.

Vote on proposal:

 Yea: SDC, AJH, DC, LMS, MKP; RDO reluctantly

 Nay: O

 Abstention: BDB

2. SDC: Job for Roy:

 -Reintroduce pink warning markers (or make it show, not currently showing)

 -Rationale for proposals & changes--where do these show up? where can be seen? (doesn’t show in “History”)

3. Society of Enoch: Carrying on this use: Son of man and two witnesses taken up into heaven. The use is more than publishing a book: it is preserving the Word.

4. Bringing Brett up to speed: work on list of waiting proposals

5. Andy will work on footnote for *jeduthun*

6. Lawson will find reference about devil and satan-- see also AE 120:2--put it into vocabulary