KEMPTON PROJECT MEETING

MARCH 1, 2018

PRESENT: AJH, LMS, RDO, MKP, SDC by Skype

1. TIMETABLE QUESTIONS.

Timetable as of 2016:

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

**“KEMPTON PROJECT TIMETABLE FOR PUBLICATION**

**as of August 12, 2016**

1. Get NT & Psalms to proofers **no later than the** **end of 2016**: in 3or 4 parts, Psalms in one, NT in two or three

2. Have proofer corrections due on NT/Psalms, each chunk due back in max of two weeks; **all done by April 1, 2017**

3. **Summer 2017** spend week on \*getting OT (less Psalms) ready for printing proofer copies\*

4. Get whole OT less Psalms out to proofers by **Sept 15 2017**

5. OT corrections back from proofers **Jan. 1, 2018** (end of Christmas break); last deadline

6. Process proofer corrections **Jan. 1, 2018 through March 15** (Ides of March)

7. PDF’s to printer--They will probably need PDF’s around a 4 to 6 wks ahead of time, so deadline of **April 15, 2018**

8. Books in hand **June 1, 2018** (to have for distribution June 19, 2018)”

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

Making a new timetable:

AJH suggests we send it out in 3 chunks; most likely to be ready first is historicals (bigger section), then the law, and the prophets.

Aim to send out

Summer 2018: historicals to proofers in 2 sections at the end of the

Spring 2019: send out the law (or prophets)

Fall of 2019: send out prophets (or law)

--This would mean all text locked by end of 2019.

Give proofreader s 2 months to get the books back & hope they get them back in 3 months

Gives us 4 (3) months to process the proofreader comments

2. Q: Did the 7’s get sorted out? 0’s are now available, AJH will sort out which 7’s need to be changed to 0’s

#1 in 2/8 agenda

“Corban” finished? Yes

#3 in 2/8 agenda

Luke 8:14--fell among? into? thorns

Proposal:

#5 in 2/8 agenda

rushed down a cliff (leave Rel 21:18 out of the issue for now) (Matt 8:32, Mark 5:13, Luke 8:33)

#9 in 2/8 agenda:

vocab marks--toggle marks inside quoted toggles are ignored, but vocab marks are noticed for validation

#10 in 2/8 agenda:

Gen 30:30

End of 2/8/18 agenda items.

Psalms beginning verse: of Solomon. Make it consistent, to have: , of Solomon….

Heather King question for school (and DC) about printed copies for June 19:

AJH: maybe print up NT & Psalms to give to them; will make it so they can use it at school, but also leave it to parents to get the whole Word (or not) as they wish.

Roy--can you find out price to print it (in place of Word box)? (At a guess--hard bound perfect binding is about $15 per book)

Lawson will talk to Heather as to whether that would be acceptable.

Worked on List of Proposals

Matt. 15:18 The\_things, these\_things: Andy would like a note in Green Book, that when these occur, the word “things” is being added. Middle-size italics.

[MKP would like to discuss middle sized italics at some point.]

Luke 4:18

Brings up the question of Gk aphesis--forgive? remit? (release, here?)

Inconclusive