KEMPTON PROJECT

SEPT. 17, 2018

RDO, JDC, DC, LMS, SDC, AJH, MKP

1. **TIME LINE**—discussion sparked by Karen email about time line and flow chart.

Psalms and NT—done, locked.

Joshua & Kings (Historicals)—due Sept 22

What order to do the last 2?

Law (Moses)

Prophets

Law will be simpler in vocab, Prophets more difficult; do easier one first?

[SDC: Stave/staff toggle question heads up]

DC tabulation on comments in Prophets & Law

PROPHETS

Pink & unclassified comments 466—355 of these are pink

LAW

525 comments, 123 pink

-->>DECISION—UNANIMOUS: DO PROPHETS THEN LAW

Start with harder one and get started on that first. If we do that we will have more time total on the Prophets—can go on working on it while

2. For reference: Timetable from March 2018, adjusted:

**“*TIMETABLE IN BRIEF****, FROM MARCH 1, 2018:*

*SUGGESTED:3 MORE CHUNKS, HISTORICALS, LAW, AND PROPHETS..*

***SUMMER 2018****: HISTORICALS TO PROOFERS IN 2 SECTIONS AT THE END OF THE SUMMER [Sept. 22]*

***SPRING 2019****: SEND OUT THE PROPHETS*

***FALL OF 2019:*** *SEND OUT LAW*

*ALL TEXT LOCKED BY END OF 2019.*

*GIVE PROOFREADERS 2 MONTHS TO GET JOB DONE, HOPE THEY GET THEM BACK IN 3 MOS.*

*GIVES US 4 (3) MONTHS TO PROCESS THE PROOFREADER COMMENTS”*

We will spend time at next meeting honing the timetable—

 PUT ON AGENDA FOR NEXT MEETING

3. We spent rest of meeting addressing pink comments in historicals