KEMPTON PROJECT MEETING

10/1/18

RDO, JDC, DC, LMS, SDC, AJH, MKP

1. SCHEDULE

Revisiting the schedule—new timeline needed—prompted by comments by Karen, that proofreading needed after it goes to the printer.

Roy took a crack at a new timeline but wasn’t sure of his figuring, but it looked as if not time to get it to printer by June 19, 2020.

Isn’t ready to go into details.

If send out Prophets beginning of Jan. and Law in April, then wd have it all back by summer meeting and have time to incorporate proofer input. Last time it took a year to process all the proofer comments; we have 3 sets in 13 months to get done. We have to be processing as we go, not wait until all the sections come in.

Paper: weight is given per thousand printer sheets (2 reams)

2. Comments

DC suggests someone goes through the brown ones for the Prophets and sort out which are really pink. Then deal with as a group.

3. glory/ honor

Andy use [\*give] glory not give\_glory

4. Problem with capitalization, e.g. Ezek 37:4: Word, word

 Again He said unto me, Prophesy upon these bones, and say unto them, O ye dry bones, hear the word of Jehovah.

Calendar for next month: next meeting Oct 15